## Sheet1
B2D - OPEN vs. CLOSED ISSUE TRACKER 2022 |  |  |  | New issues ADDED in last 24 hour |  | Issues DONE in last 24 Hour |  | Sheet last update on
|  |  |  | 1 |  | - |  | 09:11 09:11
Ref No | ISSUE | TYPE | PRIORITY | OPENED | BY | CLOSED | FOR | Comments | Estimated Date
2 | Issue: Stock Mismatch Reported by ASM - Aman Narang Distributors have stock of some sku but SA is not able to punch order in app . These 2 distributors are- 1.Shri shashiraj group 2.H S Trading co | Order placing error | Medium | 2022-03-01 | VT | Pending | GR |  | Mention
3 | Issue: DB Physical V/s System Stock Not Match 1) KP Enterprise 2) Patel Enterprise | Stock Mismatch | Medium | 2022-03-01 | VT | Pending | GR |  | Mention
4 | DB: AMAR INDUSTRIES Below Load IDs are physically 'Delivered' to DB, But in system still showing as 'Shipped': L23BW000005737 L27BW000304340 Because of this DB is unable to Inward the Stock. These were Delivered to DB on 20/Dec It's been more than 10 days these Load IDs are still in Shipped status. | Load ID Status Update | High | 2022-03-01 | VT | Pending | GR |  | Mention
6 | DB: KNJ AGENCY Load ID: L06BW000180595 Yesterday this load is physically Delivered to DB But still in system the Load status is 'Shipped' because of this DB is unable to Inward. | Load ID Status Update | High | 2022-05-01 | VT | Pending | GR |  | Mention
7 | This is a new DB who received Physical stock on 05/Jan DB Login: harshitm37@gmail.com Password: Agra@123 Issue: Stock mismatch in Product ID - 2874157 | Stock Mismatch | Medium | 2022-07-01 | VT | Pending | GR |  | Mention
10 | DB Login: KESHAVDISTRIBUTOR2016@gmail.com Pass: Sanjeev@1 Below product is Inwarded with below Qty against below Load IDs: Product ID: 9507903 L23BW000005974: 12000 L27BW000286388: 480 L27BW000296179: 7200 Total Inwarded Qty: 19680 Only one Retailer order placed with for this item: Order ID: 22IA120255368973 Ordered Qty: 880 Now in stock report it is showing available Qty as: 320 And same msg SA is facing while placing Retailer order for more than 320 Qty. In this scenario there is a very Huge difference in Qty....Seems that our 'Inward Stock' option is not working properly. | Inward Issue | Medium | 2022-11-01 | VT | Pending | GR |  | Mention
11 | Getting error while placing DB order. DB Login: nandajitds@gmail.com Pass: Dinesh@9020 | Order placing error | High | 2022-12-01 | VT | Pending | GR |  | Mention
13 | DB Login: medox.marketing@gmail.com Password: Ritu@123 Product ID: 9507903 B2D Order ID: 22MA1412809065 POID: 843922R92B944 DB placed this order and automatically it got updated as 'Cancelled' and showing Qty as Zero. | Order Auto Cancelled | Medium | 13-01-2022 | VT | Pending | GR |  | Mention
14 | DB Login: shreeajmeedjitraders@gmail.com Pass: India@123 SA Login: vishal.kasbe@brandbees.in Pass: India@123 Product ID: 9507908 DB has 9840 Qty for this product but still this is not visible to SA for Retailer ordering. | Product not visible to SA | Medium | 13-01-2022 | VT | Pending | GR |  | Mention
15 | Graph showing wrong Retailer Count - Login: jay.prakash@brandbees.in Pass: shivu@12345 Login: pawan.sharma@brandbees.in Pass: Prano#2014 ASM: Vishal Bhatia Login: vishal.bhatia@brandbees.in Pass: Lovish@11 | Graph showing wrong retailer count | Medium | 17-01-2022 | VT | Pending | GR |  | Mention
18 | DB Login: KESHAVDISTRIBUTOR2016@gmail.com Password: Sanjeev@1 Order ID: 21P40571542440 On order Detail view 'Total Price' is Zero | Incorrect DB total Amount | High | 17-01-2022 | VT | Pending | GR |  | Mention
20 | DB Login: madanlongani@gmail.com Pass: Hari@1975 Physical stock available with DB but not available in system for Retailer ordering: 9507913 9507903 9507898 Please reconcile the Stock for this DB on priority. | Stock reconcile | Medium | 17-01-2022 | VT | Pending | GR |  | Mention
22 | DB Name: Ruhani Agencies Virtual Acc#: 9999BD7025 DB Name: Jai Durga Virtual Acc#: 9999BD6887 Issue: By mistake 'Ruhani Agencies' has made payment of Rupees (₹221000+ ₹19000 = ₹250000 total) to virtual acc# '9999BD6887' instead of their own virtual acc# '9999BD7025' Shailesh Ji has already did this transfer entry in the acc# '9999BD7025' and entry reflected under 'Ruhani Agencies'. However, the same entry is not reflecting in our B2D system under 'Ruhani Agencies'. This payment is still showing under 'Jai Durga' Please make required corrections. | Payment in wrong Account | High | 17-01-2022 | VT | Pending | GR |  | Mention
24 | Issue while generating the bill of R K Trading Ajmer .product ID :-9507909 multiple codes stock reduction is deducting in double quantity (Same as ref no 242) | Stock Report Item Deduction | High | 18-01-2022 | VT | Pending | GR |  | Mention
25 | DB Login: jaidurgaagencies786@gmail.com Password: Naman@123 B2D Order ID: 22IA125512539474 POID: 833422NB36FFD, 833422N0CC55B On both of these POIDs I have found below comments: Last Modified By: autocancel@firstcry.com Action: Cancel Order Action Time: 16-01-2022 22:38:52 Comments: Order status set to Cancelled due to payment disapproval. However, the amount was present in DBs account then why these orders are 'Cancelled'? | Order Auto Cancelled | Medium | 18-01-2022 | VT | Pending | GR |  | Mention
26 | DB Name: Bhatia Kheti Store SE Login: kumar.amit1@brandbees.in Pass: Welcome@123 >> This SE is mapped with this DB SA Login: ext.prabhjeet.singh@brandbees.in Pass: Welcome@123 SA Login: ext.harjodh.singh@brandbees.in Pass: Welcome@123 >> These SAs are mapped with above SE Issue: While creating Retailer 'Select Distributor' dropdown is empty. In past these SAs had successfully created Retailers under this DB Plz check & fix. | Select Distributor dropdown is Empty for SA | High | 18-01-2022 | VT | Pending | GR |  | Mention
27 | Stock reconcile for DB Bonanza | Stock reconcile | Medium | 19-01-2022 | VT | Pending | GR |  | Mention
28 | CH Login - CN should show company Name One CN is of zero value | CN Screen modification | Medium | 19-01-2022 | VT | Pending | GR |  | Mention
29 | DB Name: AMAR INDUSTRIES DB Login: amar.gsk@gmail.com Password: Amar@123 As discussed - Margin amount is incorrect. | Incorrect Margin Amount | High | 19-01-2022 | VT | Pending | GR |  | Mention
31 | Issue: Retailers of different Cities & DBs are reflecting under this SA: ext.aniket.sapkal@brandbees.in SE: vishal.tiwari1@brandbees.in is mapped with DB: KRISHNA ENTERPRISES (mathuraent2707@gmail.com). SA: ext.aniket.sapkal@brandbees.in is mapped with this SE: vishal.tiwari1@brandbees.in | Different city Retailer are reflecting | Medium | 21-01-2022 | VT | Pending | GR |  | Mention
34 | Reconcile Stock for DB: Anuj Medicos Sir Super dry pant M1 not showing in SA tab Stock is present in godown | Stock reconcile | Medium | 22-01-2022 | VT | Pending | GR |  | Mention
35 | DB Login: amar.gsk@gmail.com Pass: Amar@123 B2D Order ID: 22LB238352112786 Issue: Difference Ordered Qty Vs Fullfield Qty Issue initially happeded on B2D order is: 22JB2412660812731 (I cancelled this order and placed a new order: 22LB238352112786) Product ID '9507897' was added to Cart with 3360 not sure why system showing fulfilled Qty as: 6720 Gap Quantity: -3360 Also, same item is added twice in this order. | Difference Ordered Qty Vs Fullfield Qty | Medium | 24-01-2022 | VT | Pending | GR |  | Mention
37 | S1 stock is Not showing in Om sai Trading kindly help and resolved Product ID: 9507898 Physical Stock: 6000Pcs Please reconcile stock for DB: omsaienterprises9000@gmail.com | Stock reconcile | Medium | 25-01-2022 | VT | Pending | GR |  | Mention
38 | S1 stock is Not showing in DB: Bhatia Kheti Store Product ID: 9507898 Plz reconcile the Stock | Stock reconcile | Medium | 25-01-2022 | VT | Pending | GR |  | Mention
39 | 1) ASM (Mayur) has requested data export of Beat details in a CSV/XLS format. The file should have below columns in it: SE Email ID Beat Name Occurrence Type Occurrence Day Users / SA Email ID Retailer's Company Name Retailer's City 2) Also, the Beats should be Visible to ASM, RSM & Meghashyam. Currently it is only visible to the User who has created the Beat. 3) And we should also give a option to export Beat details. | Beats Report | Medium | 25-01-2022 | VT | Pending | GR |  | Mention
40 | Transfer all 'Retailers & Beats' from SA: ext.Ravi.Sangani@brandbees.in to SA: ext.dhaval.jani@brandbees.in | Beats - SA mapping | Medium | 27-01-2022 | VT | Pending | GR |  | Mention
41 | DB/Business Type: RGT DB Name: Shree Sai Distribution DB Login: sureshbmandhare@gmail.com Pass: Sai@mh12 DB Order placed by SE: vishal.tiwari@brandbees.in via 'https://admin.brandbees.in/': The same Order is not visible on DB portal: | Order not visible | Medium | 27-01-2022 | VT | Pending | GR |  | Mention
42 | DB Login: patelenterprise1994@hotmail.com Pass: Patel@123 The Product ID: 9507897 is Inwarded in the system via below load ID: Load ID: L23BW000006041 ¦ Qty: 1200 In DB Stock report as well this item is showing Qty as: 1200 Issue: This products is not displaying when SA is trying to place Retailer order. | Product not visible to retailer | Medium | 27-01-2022 | VT | Pending | GR |  | Mention
44 | Business Type: RGT DB Login: rudraent.connect@gmail.com Password: Rudra@123 Issue: Yesterday, DB had made payment but it is still not reflecting in DB's Live ledger: | Payment not reflecting in Ledger | High | 28-01-2022 | VT | Pending | GR |  | Mention
45 | DB/Business Type: RGT DB Name: Shree Sai Distribution DB Login: sureshbmandhare@gmail.com Pass: Sai@mh12 DB Order placed by SE: vishal.tiwari@brandbees.in via 'https://admin.brandbees.in/' The same Order is not visible on DB portal. | Order not visible | High | 28-01-2022 | VT | Pending | GR |  | Mention
46 | DB: Gandhi Agencies - Jalandhar Issue: Below products physical stock is available with DB. But in system & stock report the Qty is Zero: 9507898 9507913 9507897 9507903 | Stock reconcile | Medium | 28-01-2022 | VT | Pending | GR |  | Mention
47 | Refer email with Sub: Re: Secondary Gap between Portal vs Reported - SS Marketing - Agra As discussed earlier, we suggested steps to the team to enter differential Secondary sales orders in our B2D system. But while punching those orders team is getting errors as: Out of Stock or Can't place more than specific Qty | Secondary Gap between Portal vs Reported | Medium | 28-01-2022 | VT | Pending | GR |  | Mention
48 | 1) As Per 28th Jan 2022 Stock Report Superdry 1pc M Size Total Stock Was 915 pc After 190 pc bill stock is 0 Now. DB Name :- KP Enterprise DB User Id :- kpenterprise409@gmail.com Password :- Krunal@123 2) As Per 28th Jan 2022 Stock Report Superdry 1pc M Size Total Stock Was 1465 pc After 640pc bill stock is 0 Now. DB Name :- Patel Enterprise DB User Id :- patelenterprise1994@hotmail.com Password :- Patel@123 Kindly reconcile the stock for these 2 DBs. | Stock reconcile | Medium | 31-01-2022 | VT | Pending | GR |  | Mention
50 | Stock mismatches found in below DBs. Please reconcile the stock. gandhiagencies1@gmail.com (Gandhi Agencies) samtaagarwal001@gmail.com (SHRI RISHABH AGENCY) ashokgehlot1@gmail.com (MAHENDRA DISTRIBUTORS) | Stock reconcile | Medium | 31-01-2022 | VT | Pending | GR |  | Mention
52 | DB Login: omsaienterprises9000@gmail.com Pass: India@123 Issue: When Accepting/Confirming Retailer order the 'Total Item & Qty' changing to Zero. | Incorrect Total Itm, Qty while accepting order | Medium | 2022-01-02 | VT | Pending | GR |  | Mention
53 | SE Rumaan reported that his SAs are unable to open the first Beat in their list. SA Login: ext.obaid.manzoor@brandbees.in Pass: Welcome@123 | Beats not opening | Medium | 2022-01-02 | VT | Pending | GR |  | Mention
56 | SA Yawar has around 80 retailers already added in the portal but the dashboard shows 67 retailers. SA Login: ext.yawar.shabir@brandbees.in Password: Welcome@123 | Dashboard - Wrong Count | Medium | 2022-04-02 | VT | Pending | GR |  | Mention
57 | Stock Received at DB Point on last Friday (28/Jan) But Still Load ID Status is "Shipped". Coz of this DB is unable to inward the Stock. DB Name - Creative Enterprise DB Login: viratshah1983@yahoo.com Password: Virat@123 | Unable to Inward | Medium | 2022-04-02 | VT | Pending | GR |  | Mention
58 | Login Dashboard showing error on graphs | Dashboard Error | Medium | 2022-04-02 | VT | Pending | GR |  | Mention
59 | Team is getting error on: 1. Customer > List page 2. Products > List page | Admin Page Error | Medium | 2022-06-02 | VT | Pending | GR |  | Mention
60 | DB Email :- kpenterprise409@gmail.com Product ID :- 9507903 Current B2D System Qty :- 0 Total Purchase Qty :- 4800 System Billing Qty :- 1960 Current Physical Qty with DB :- 2840 DB Email :- patelenterprise1994@hotmail.com Product ID :- 9507903 Current B2D System Qty :- 0 Total Purchase :- 4800 System Billing Qty :- 480 Current Physical Qty with DB :- 4320 Please reconcile the Stock only for these 2 products IDs for respective DBs as mentioned above. As per SE remaining Stock is correct in the system only these 2 products have stock issue. Kindly resolve this on Priority. | Stock reconcile | Medium | 2022-06-02 | VT | Pending | GR |  | Mention
61 | Reconcile Stock for DB: Right Medical Store Super dry pant M1 not showing in SA tab Stock is present in godown. | Stock reconcile | Medium | 2022-07-02 | VT | Pending | GR |  | Mention
64 | Same product is listed multiple times. This is currently being faced by all SAs. | Product Listing | Medium | 2022-09-02 | VT | Pending | GR |  | Mention
66 | Please move all Retailers & Beats: From SA 'ext.rishab.narang@brandbees.in' And DB 'ombalajitraders12@gmail.com' To SA 'ext.gourav.arora@brandbees.in' And DB 'medixpertz.dist@gmail.com' | SA - Beat - DB update | Medium | 2022-10-02 | VT | Pending | GR | VT: Followup on 14/02/2022 | Mention
68 | RSM Vinay getting below error on 'Order > List' page: Login: vinay.doegar@brandbees.in Pass: Shree@2141 | Admin - Order List error | Medium | 2022-10-02 | VT | Pending | GR |  | Mention
69 | Refer email with Sub: Request to shift/assign retailers Please shift/move all 'Retailers & Beats' from existing to New SAs >From SA Email ID To New SA Email ID ext.ajay.lokhande@brandbees.in ext.mahesh.maurya@brandbees.in ext.krishna.singh@brandbees.in ext.akash.kumar@brandbees.in ext.sagar.dabade@brandbees.in aniket.sapkal@brandbees.in gagan.acharya@brandbees.in ext.jitendra.chavan@brandbees.in kiran.koli@brandbees.in ext.amar.balla@brandbees.in | SA - Beat - Retailer update | Medium | 2022-11-02 | VT | Pending | GR |  | Mention
69 | DB Login: bonanza782013@gmail.com Password: Vipul@123 Issues: On Cart page: 1. Place Order button is disabled. 2. Case & Product Qty is not visible | Cart Page | High | 14-02-2022 | VT | Pending | GR | not recieved task done update | Mention
70 | Please update this correct GST number in B2D system. Franchise/DB Name: MALTI ENTERPRISES FCFID - 8535 Current GST#: 27CVZPM2206CIZH Correct GST#: 27CVZPM2206C1ZH | B2D: GST No. Update | Medium | 14-02-2022 | VT | Pending | GR | not recieved task done update | Mention
71 | ssue: Product Prices are Zero upon WholeSeller login. RGT DB Login: um_dec12@yahoo.com Password: Unique@123 WholeSeller Login: Royalsalesdepo17@gmail.com Password: Royal@123 WholeSeller Login: jineshgandhi07@gmail.com Password: Jinesh@123 | Product Price issue | High | 14-02-2022 | VT | Pending | GR | not recieved task done update | Mention
72 | Refer this msg from 11/Feb We need to shift/assign all the 'Retailers & Beats' from existing SAs to these New SA IDs. | Reassign SA Beat and Retailer | High | 15-02-2022 | VT | Pending | GR
73 | Please Reconcile Stock for below DB: DB Name: S.R INTERNATIONAL DB Email: srinternational91@gmail.com Product Name purchase qty sale qty miss qty Babyhug Super Dry Pant Style Diaper Medium - 1 Piece 12000 1440 10560 Babyhug Super Dry Pant Style Diaper Small - 1 Piece 3600 1440 2160 Babyhug Super Dry Pant Style Diapers Extra Large - 26 Pieces 18 9 9 Babyhug Super Dry Pant Style Diapers Large - 34 Pieces 30 18 12 | Stock reconcile | medium | 15-02-2022 | VT | Pending | GR |  | Mention
74
75