## Sheet1
S No. | Task | Priority | Estimation Efforts(including the DEV+QA) | Go Live Date | Comment
1 | QPS Scheme Implementation(without SR ) | 1 | 10 Working Days | 2022-06-01
2 | UI :User Dashboard - with Sales and Stock Reports | 1 | 35 Working days | 2022-07-01 | Dependancy on API development.
API :User Dashboard - with Sales and Stock Reports
3 | USER ONBOARDING :MT - Retailer OnBoarding Flow (With Different Margins at Retailer level) | 1 | 24 Working Days | 2022-06-20 | Updated CR document Requested to Product Team
ORDERING: MT- Retailer Onboarding Flow(with differnt marging at retailer level)
4 | Bulk Reallocation: Beat reallocation from Old SA to New SA in Bulk. | 2 | NA | 2022-05-17 | Deployment Pending
5 | Fix error on Invoice on 'Inward Stock' page: | 1 | 6 working days | 2022-05-24 | QA will test on Live environment
Error: Request failed with status code 400
6 | B2D - Scheme CN Questions & Requirement | 1 | 8 working days | 2022-06-06 | CR
1. Enable the View access of 'CN > List' for Roles: SE, ASM, RSM
So that these roles can view the weekly CN amount and should also be able to download the SKU wise CN report as well.
| 2. Need the option to download one consolidated CN report for all DBs.(ADMIN ) |  | 4 working days
| 3. Same Scheme CN report should be available in the DB portal 'https://brandbees.in/' along with the same date range filters (Yearly, Monthly & Weekly). |  | 9 working days
| 4. CN Invoice: On Live Ledger, the 'Credit Note' entry should be clickable and upon clicking it should download the CN document. |  | 4 working days
7 | Deletion and Replacement of DB - Old to new DB | 2 | Req. Document pending |  | Document Pending
8 | Beat Enhancement | 2 | Req. Document pending | - | Document Pending
9 | Beat data extraction facility, export | 2 | Format pending from Product Team | - | Format pending from Product Team
10 | SA – Day end performance report | 2 | Req. Document pending | - | Document Pending
11 | DB - Stock Audit process | 2 | Req. Document pending | - | Document Pending
12 | Sampling Flow - DB should be able to order samples. | 2 | Req. Document pending | - | Document Pending